## Project_Plan
Select→ | Daily |  | Highlight Date | 2018-08-04 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-04 | 2018-08-05 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-11 | 2018-08-12 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 2018-08-18 | 2018-08-19 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-25 | 2018-08-26 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 2018-09-01 | 2018-09-02 | 2018-09-03 | 2018-09-04 | 2018-09-05 | 2018-09-06 | 2018-09-07 | 2018-09-08 | 2018-09-09 | 2018-09-10 | 2018-09-11 | 2018-09-12 | 2018-09-13 | 2018-09-14 | 2018-09-15 | 2018-09-16 | 2018-09-17 | 2018-09-18 | 2018-09-19 | 2018-09-20 | 2018-09-21 | 2018-09-22 | 2018-09-23 | 2018-09-24 | 2018-09-25 | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05
Activity | Start Date | End Date | Duration | Status | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-04 | 2018-08-05 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-11 | 2018-08-12 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 2018-08-18 | 2018-08-19 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-25 | 2018-08-26 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | 2018-09-01 | 2018-09-02 | 2018-09-03 | 2018-09-04 | 2018-09-05 | 2018-09-06 | 2018-09-07 | 2018-09-08 | 2018-09-09 | 2018-09-10 | 2018-09-11 | 2018-09-12 | 2018-09-13 | 2018-09-14 | 2018-09-15 | 2018-09-16 | 2018-09-17 | 2018-09-18 | 2018-09-19 | 2018-09-20 | 2018-09-21 | 2018-09-22 | 2018-09-23 | 2018-09-24 | 2018-09-25 | 2018-09-26 | 2018-09-27 | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05
Activity 01 | 2018-08-01 | 2018-08-05 | 4 | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress
Activity 02 | 2018-08-05 | 2018-08-07 | 2 | Completed |  |  |  |  | Completed | Completed | Completed
Activity 03 | 2018-08-07 | 2018-08-10 | 3 | Completed | [6 empty] | Completed | Completed | Completed | Completed
Activity 04 | 2018-08-11 | 2018-08-20 | 9 | Completed | [10 empty] | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Activity 05 | 2018-08-18 | 2018-08-22 | 4 | Completed | [17 empty] | Completed | Completed | Completed | Completed | Completed
Activity 06 | 2018-08-21 | 2018-08-25 | 4 | Completed | [20 empty] | Completed | Completed | Completed | Completed | Completed
Activity 07 | 2018-08-26 | 2018-08-30 | 4 | In Progress | [25 empty] | In Progress | In Progress | In Progress | In Progress | In Progress
Activity 08 | 2018-08-30 | 2018-09-05 | 6 | In Progress | [29 empty] | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress
Activity 09 | 2018-09-05 | 2018-09-18 | 13 | In Progress | [35 empty] | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress
Activity 10 | 2018-09-18 | 2018-09-25 | 7 | Pending | [48 empty] | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
Activity 11 | 2018-09-26 | 2018-09-30 | 4 | Pending | [56 empty] | Pending | Pending | Pending | Pending | Pending
Activity 12 | 2018-09-28 | 2018-10-05 | 7 | Pending | [58 empty] | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
Dynamic Project Plan (Gantt Chart) WWW.PK-AnExcelExpert.Com