## Gantt Chart
|  | Highlight |  | 2017-10-12
Activity | Start Date | End Date | Duration | Status | 2017-10-01 | 2017-10-02 | 2017-10-03 | 2017-10-04 | 2017-10-05 | 2017-10-06 | 2017-10-07 | 2017-10-08 | 2017-10-09 | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-14 | 2017-10-15 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-21 | 2017-10-22 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-28 | 2017-10-29 | 2017-10-30 | 2017-10-31
Activity 01 | 2017-10-01 | 2017-10-10 | 10 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Activity 02 | 2017-10-04 | 2017-10-10 | 7 | Pending |  |  |  | Pending | Pending | Pending | Pending | Pending | Pending | Pending
Activity 03 | 2017-10-07 | 2017-10-11 | 5 | Completed | [6 empty] | Completed | Completed | Completed | Completed | Completed
Activity 04 | 2017-10-10 | 2017-10-16 | 7 | Completed | [9 empty] | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Activity 05 | 2017-10-10 | 2017-10-21 | 12 | Pending | [9 empty] | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
Activity 06 | 2017-10-16 | 2017-10-18 | 3 | Completed | [15 empty] | Completed | Completed | Completed
Activity 07 | 2017-10-19 | 2017-10-22 | 4 | Pending | [18 empty] | Pending | Pending | Pending | Pending
Activity 08 | 2017-10-22 | 2017-10-26 | 5 | Completed | [21 empty] | Completed | Completed | Completed | Completed | Completed
Activity 09 | 2017-10-25 | 2017-10-29 | 5 | Pending | [24 empty] | Pending | Pending | Pending | Pending | Pending
Activity 10 | 2017-10-28 | 2017-10-31 | 4 | Pending | [27 empty] | Pending | Pending | Pending | Pending
Project Plan
Click to Learn KPI Indicators with Excel Cells
Click to learn a Progress Circle Chart in chart in excel
0
PK:
An Excel Expert

## Sheet6
|  | Highlight |  | 2017-10-05
Activity | Start Date | End Date | Duration | Status | 2017-10-01 | 2017-10-02 | 2017-10-03 | 2017-10-04 | 2017-10-05 | 2017-10-06 | 2017-10-07 | 2017-10-08 | 2017-10-09 | 2017-10-10 | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-14 | 2017-10-15 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-21 | 2017-10-22 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-28 | 2017-10-29 | 2017-10-30 | 2017-10-31
Activity 01 | 2017-10-01 | 2017-10-05 | 5 | Pending | Pending | Pending | Pending | Pending | Pending
Activity 02 | 2017-10-04 | 2017-10-10 | 7 | Pending |  |  |  | Pending | Pending | Pending | Pending | Pending | Pending | Pending
Activity 03 | 2017-10-07 | 2017-10-11 | 5 | Completed | [6 empty] | Completed | Completed | Completed | Completed | Completed
Activity 04 | 2017-10-10 | 2017-10-16 | 7 | Completed | [9 empty] | Completed | Completed | Completed | Completed | Completed | Completed | Completed
Activity 05 | 2017-10-10 | 2017-10-14 | 5 | Pending | [9 empty] | Pending | Pending | Pending | Pending | Pending
Activity 06 | 2017-10-16 | 2017-10-18 | 3 | Completed | [15 empty] | Completed | Completed | Completed
Activity 07 | 2017-10-19 | 2017-10-22 | 4 | Pending | [18 empty] | Pending | Pending | Pending | Pending
Activity 08 | 2017-10-22 | 2017-10-26 | 5 | Completed | [21 empty] | Completed | Completed | Completed | Completed | Completed
Activity 09 | 2017-10-25 | 2017-10-29 | 5 | Pending | [24 empty] | Pending | Pending | Pending | Pending | Pending
Activity 10 | 2017-10-28 | 2017-10-31 | 4 | Pending | [27 empty] | Pending | Pending | Pending | Pending